## 20-Week Plan
Cohort 2 ¦ 20-Week Plan (revised post placement review)
Start 28 Sep. 510 hrs / 33 credits, unchanged. Builds at 3/6/9/12/15; exams after 5/10/15. Foundations run data-analysis-led. One goal: placement.
Wk | Focus | Main content | Assessment beat | Role emphasis
1 | Data analysis foundations | Python through data; descriptive statistics; hypothesis testing and inference; correlation vs causation; insight communication | Daily Kahoot; AI-free lab | Analyst / DS
2 | Data manipulation at depth | SQL joins and window functions; join semantics and validation; pandas groupby, merge, reshape; one Excel-for-analysts day | Weekly proctored coding | Analyst / DS
3 | BUILD 1: Data-to-Insight | Named-customer brief on raw messy data; insight set; challenges log; live demo | Mock R1 + GD + case study | Analyst / FDE
4 | Business and data analyst craft | Business metric design; market basket, lift, cross-sell; cohort and funnel; forecasting basics; cross-domain transfer drill | Business case study (AI-free) | Analyst / BA
5 | Machine learning core + ME1 | Regression and classification; the metric trap; feature engineering and leakage; overfitting and regularisation; model justification | ME1: stats, data, analyst, ML | DS / AI Eng
6 | BUILD 2: ML mini | Named-customer ML brief with an injected constraint; honest evaluation; recommendation; live demo | Mock R2 + GD | DS / FDE
7 | Deep learning essentials | Neuron and network; backprop intuition; optimisers and training dynamics; debugging a training run; the bridge to next-token prediction | Weekly proctored coding | AI Eng
8 | Transformers and LLM internals | Tokenization; attention and self-attention; embeddings; decoding controls; context windows and token economy | Bi-weekly assessment | AI Eng
9 | BUILD 3: DL / LLM mini | Named-customer LLM brief; debug a broken training loop AI-free; controlled outputs; live demo | Mock R3 + GD | AI Eng / FDE
10 | Generative AI applied + ME2 | Prompt patterns and system prompts; structured and constrained outputs; function calling; prompt evaluation; cost and latency | ME2: DL, transformers, LLM, GenAI | GenAI Eng
11 | Retrieval-augmented generation | Chunking trade-offs; embedding and vector store choice; hybrid search and reranking; RAG evaluation; citations and grounding | Weekly proctored coding | GenAI Eng
12 | BUILD 4: RAG mini | Knowledge-base RAG with mandatory citations; evaluation harness with reported numbers; live demo | Mock R4 + GD | GenAI Eng / FDE
13 | AI agents | Tool use and tool schema design; ReAct, plan-and-execute, reflection; memory and state; controlled flows; agent failure modes | Bi-weekly assessment | Agentic Eng
14 | Agents in production | Trajectory evaluation; guardrails for injection, PII and budget; checkpointing, retries, idempotency; cost-latency-quality; deployment and observability | Weekly proctored coding | Agentic Eng
15 | BUILD 5: Agentic mini + ME3 | Evaluated, guarded agentic system for a named customer; two-round mock simulation | Mock R5 + ME3: RAG, agents, production | Agentic Eng / FDE
16 | Forward deployed engineering + capstone kickoff | Business problem framing; solution thinking and disqualification; alternatives and trade-off metrics; quantified option evaluation; POC vs MVP pitch with options A, B, C | Solution pitch (assessed) | FDE
17 | Capstone sprint 1 | Architecture and core build with evaluation baked in; mentor checkpoint; FDE application simulations continue | Capstone checkpoint | FDE / AI Eng
18 | Capstone sprint 2 + demo prep | Feature completion, deployment, documentation; demo rehearsal and live-defence drills; portfolio polish | Capstone review | All
19 | Demo Day + placement start | Industry panel demo; JD-driven domain prep begins; HR and behavioural coaching intensive; active interviews | Demo Day | All
20 | Placement + final mocks | External panel mocks; interview funnel management; company-specific case prep; offer support | Final mocks | All
Build weeks (shaded): no new content. Mini-project on a named-customer brief, mock interview with half the time as a project viva, impromptu group discussion, offline presentation and a live demo. All grades close in-week.
Week 16 (blue) is the Forward Deployed Engineering block, roughly 30 hours, running into the capstone so the capstone is scoped and pitched in FDE mode. FDE method is also the operating mode of every build week.
Machine learning essentials are supported by a pre-work bridge course, so classroom time in Wk5 weights toward doubt-clearing and application. Computer Vision is deliberately excluded.

## Detailed Curriculum
Cohort 2 ¦ Detailed Curriculum, sub-topic level
Every week: topic clusters, sub-topics, and what the student produces or is drilled on.
Topic cluster | Sub-topics | Output / drill
Week 1 ¦ Data analysis foundations
Python in service of data | Files and I/O; loops and comprehensions; functions and modularity; error handling and defensive code; reading a traceback | AI-free lab
Load, clean, profile | Reading messy real files; missing values; mixed and wrong types; duplicates; outlier detection; profiling before analysing | Profiled dataset
Descriptive statistics | Central tendency and spread; distributions and skew; sampling and sample size; when an average misleads | Segment summary
Inference and testing | Hypothesis testing; p-values and significance; confidence intervals; choosing the right test; practical vs statistical significance | A/B read
Causal reasoning | Correlation vs causation; confounders; Simpson's paradox; what a fair comparison requires | Cause-effect note
Insight communication | Turning a finding into a stakeholder statement; the one-number answer; choosing the right visual | Insight writeup
Week 2 ¦ Data manipulation at depth
SQL core | SELECT, WHERE, GROUP BY, HAVING; ordering and limiting; readable query structure; CTEs and subqueries | Extraction query
Join semantics | INNER vs LEFT vs OUTER; what each drops or duplicates; imperfect keys; fan-out and row-count validation; merge vs join in pandas | Joined dataset with checks
Window functions | ROW_NUMBER, RANK, DENSE_RANK; LAG and LEAD; PARTITION BY; running totals and rankings within segments | Ranking query
Pandas at depth | groupby and agg; reshape and pivot; multi-source merges; chained transformations; performance basics | Feature table
Tool judgment | SQL vs pandas vs Excel and when each is right; one Excel-for-analysts day covering pivots, lookups and presenting a number | Tool-choice note
Live drill | Three datasets on screen, produce the answer on the spot and explain the join choice | Timed SQL drill, AI-free
Week 3 ¦ BUILD 1: Data-to-Insight
The brief | Named customer, raw messy data, an open business question; scope it yourself | Scoped brief
The work | Clean, profile, analyse, test a hypothesis, segment, quantify; defend the metric you chose | Insight deck
Challenges log | What broke, what you tried, what you changed and why; recorded as you go, not written afterwards | Challenges log
Assessment | Mock R1 with half the time as a viva on this project; impromptu group discussion; offline presentation; live demo of the analysis | Mock R1, GD, demo
Week 4 ¦ Business and data analyst craft
Business metric design | What to measure and why; north-star and guardrail metrics; leading vs lagging; defining a metric so it cannot be gamed | Metric definition
Association and basket analysis | Support, confidence and lift; market basket analysis; cross-sell and upsell reasoning | Basket analysis
Cohort, funnel, retention | Cohort construction; funnel drop-off; retention curves; where the loss actually happens | Cohort study
Forecasting basics | Trend and seasonality; a naive baseline before any model; error metrics; when a forecast is good enough | Forecast baseline
Classification for business | Precision and recall trade-off set by domain; lift and gain charts; threshold selection as a business decision | Threshold memo
Cross-domain transfer drill | The same technique across healthcare, retail, hyperlocal delivery and fintech; what changes: the metric, the constraint, the cost of an error | Four-domain drill
Stakeholder communication | The one-slide answer; defending a recommendation under challenge; what to leave out | Case presentation
Week 5 ¦ Machine learning core + ME1
The modelling loop | Framing a problem as ML; train, validate, test discipline; baselines before models | Baseline model
Regression and classification | Linear and logistic; interpreting coefficients; residuals; where each fails | Two models
The metric trap | Accuracy vs precision, recall, F1; class imbalance; confusion matrix reading; choosing the metric from the business cost | Metric justification
Features | Engineering, encoding, scaling; leakage and how it hides; feature importance and its limits | Feature set
Generalisation | Overfitting and bias-variance; regularisation; cross-validation; learning curves | Tuned model
Applied breadth | Trees and clustering used, not derived; when a simpler model wins | Model comparison
ME1 | Statistics, data manipulation, analyst techniques and ML core | Major Exam 1
Week 6 ¦ BUILD 2: ML mini
The brief | Named-customer ML problem with an injected constraint such as imbalance or asymmetric error cost | Scoped brief
The work | Data to features to model to honest evaluation to a business recommendation | Working pipeline
Challenges log | The constraint you hit and how you handled it; kept live through the week | Challenges log
Assessment | Mock R2 on ML fundamentals plus project viva; group discussion; offline presentation; live demo | Mock R2, GD, demo
Week 7 ¦ Deep learning essentials
The network | Neuron, layers, forward pass; activation choice; why depth helps | Baseline net
Learning | Backprop and gradients intuition-first; loss functions; optimisers and learning rate | Training loop
Training dynamics | Reading loss curves; diagnosing non-convergence; vanishing and exploding gradients; batch size effects | Diagnosis exercise
Control | Regularisation, dropout, early stopping; reproducibility and seeds | Stabilised run
The bridge to LLMs | Next-token prediction; auto-regression; sequence modelling; why attention replaced recurrence | Concept map
Week 8 ¦ Transformers and LLM internals
Tokenization | Subwords and BPE; vocabulary; why token counts drive cost and quality; tokenizer differences across models | Tokenizer demo
Attention | Self-attention mechanics; queries, keys, values; multi-head attention; positional information | Attention walkthrough
Embeddings | Vector space and similarity; embedding models; what embeddings do and do not capture | Embedding explorer
Generation and decoding | Temperature, top-k, top-p; greedy vs sampling; determinism and reproducibility; stopping conditions | Controlled-output app
Economics | Context windows; prompt and completion cost; latency; batching | Cost model
Classical NLP | Pre-read plus one focused day: TF-IDF, word vectors and the lineage into modern models | Pre-read
Week 9 ¦ BUILD 3: DL / LLM mini
The brief | Named-customer LLM task requiring controlled, structured output | Scoped brief
AI-free segment | Debug a deliberately broken training loop with no assistant, observed | Debug drill
The work | Ship the LLM feature; measure quality and cost; document decisions | Working app
Assessment | Mock R3 on DL and LLM fundamentals plus project viva; group discussion; presentation; live demo | Mock R3, GD, demo
Week 10 ¦ Generative AI applied + ME2
Prompt engineering | System prompts; few-shot; chain-of-thought; decomposition; prompt patterns that survive model changes | Prompt library
Structured output | JSON schemas; constrained decoding; validation and repair loops; failure handling | Structured feature
Tools and function calling | Schema design; when the model should call a tool; argument validation | Tool-calling demo
Evaluating generation | Rubric and LLM-as-judge; regression suites; catching silent quality drift | Eval suite
Cost and latency in practice | Model selection by task; caching; streaming; token budget discipline | Cost review
ME2 | Deep learning, transformers, LLM internals and generative AI | Major Exam 2
Week 11 ¦ Retrieval-augmented generation
Chunking | Strategies and trade-offs; chunk size and overlap; structure-aware splitting; what breaks at each extreme | Chunking experiment
Indexing | Embedding model choice; vector databases; metadata and filtering; index refresh | Working index
Retrieval quality | Top-k selection; hybrid dense and sparse search; reranking; query rewriting | Retrieval upgrade
Evaluation | Precision@k and recall@k; faithfulness and answer relevance; building a golden set; measuring retrieval separately from generation | Eval harness
Grounding and citations | Mandatory source citation; refusal when evidence is absent; debugging right-document-wrong-answer | Cited RAG
Failure modes | Naive RAG limits; stale data; conflicting sources; long-context alternatives | Failure catalogue
Week 12 ¦ BUILD 4: RAG mini
The brief | Knowledge-base or policy-document RAG for a named customer, citations mandatory | Scoped brief
The work | Build, measure, improve; report precision@k and faithfulness with actual numbers | Evaluated RAG
Challenges log | Retrieval failures encountered and what fixed them | Challenges log
Assessment | Mock R4 on RAG design plus project viva; group discussion; presentation; live demo | Mock R4, GD, demo
Week 13 ¦ AI agents
Tool use | Tool schema design; descriptions the model can act on; argument validation; error surfaces | Tool set
Agent patterns | ReAct; plan-and-execute; reflection; router patterns; when a workflow beats an agent | Pattern comparison
Memory and state | Short and long-term memory; state persistence; context management across turns | Stateful agent
Controlled flows | Graph-based orchestration; explicit branching; human-in-the-loop checkpoints | Controlled agent
Failure modes | Loops, drift, tool misuse, silent failure; designing for observability from the start | Failure drill
Week 14 ¦ Agents in production
Trajectory evaluation | Golden trajectories; step-level accuracy; cost per task; evaluating the path and not only the answer | Trajectory eval
Guardrails | Prompt injection defence; PII handling; tool permissions and budget caps; structural limits rather than prompt pleading | Guarded agent
Reliability | Checkpointing; retries and idempotency; recovery from mid-task failure; partial completion | Self-healing flow
Cost, latency, quality | Model routing; caching; batching; where to spend and where to save | Cost-quality study
Deployment and monitoring | Beyond localhost; logging and tracing; alerting on quality regression | Deployed service
Explicitly out of scope | Platform-level orchestration and multi-agent infrastructure build-out, which sit above this hiring band | Scope note
Week 15 ¦ BUILD 5: Agentic mini + ME3
The brief | Agentic system for a named customer, evaluated, guarded and deployed | Scoped brief
The work | Ship it with trajectory evaluation and guardrails; report cost per task | Production agent
Assessment | Mock R5 as a two-round simulation plus project viva; group discussion; presentation; live demo | Mock R5, GD, demo
ME3 | RAG, agents and production | Major Exam 3
Week 16 ¦ Forward deployed engineering + capstone kickoff
Understanding the problem | Question frameworks for a client conversation; separating the stated problem from the real one; what to ask before proposing | Discovery script
Solution thinking | Open problem space to shortlist; disqualification criteria; why this and why not that | Option shortlist
Trade-off metrics | Naming what you optimise for and what you accept; quantifying options before choosing; working principles stated up front | Trade-off table
Quantified evaluation | Doing the groundwork so the recommendation carries numbers; sizing effort, cost and risk | Evaluation memo
The pitch | POC vs MVP framing; presenting option A as the recommendation with B and C as considered alternates; handling challenge | Solution pitch
Client-facing communication | Technical depth expressed in business language; managing expectations; saying no with an alternative | Simulation
Capstone kickoff | Capstone brief issued and scoped in FDE mode; architecture proposal presented as options | Capstone scope
Weeks 17-18 ¦ Capstone
Sprint 1 | Architecture and core build; evaluation designed in from the start; mentor checkpoint; FDE application simulations continue | Capstone core
Sprint 2 | Feature completion; deployment beyond localhost; monitoring; documentation | Deployed capstone
Demo preparation | Rehearsed live demo; defence drills where every decision is challenged; portfolio and README polish | Demo-ready
Challenges log | Maintained across the capstone and used directly as interview material | Challenges log
Weeks 19-20 ¦ Demo Day and placement
Demo Day | Industry panel demo and defence; portfolio finalised | Panel demo
JD-driven prep | Domain preparation against the actual job description before each interview; company and sector case prep | Per-JD prep
HR and behavioural | Talking about yourself accurately; strengths and gaps; project narrative selection; what not to oversell | Coached responses
Interview mindset | How the funnel actually works; expected conversion; treating early interviews as calibration | Funnel briefing
Final mocks | External panels, full simulation, written feedback within the week | Final mocks

## Changes vs Cohort 1
Cohort 2 ¦ Changes against the Cohort 1 curriculum
Every change traced to the placement review. This is the change record for the older curriculum.
Type | Change | What it means in delivery | Traced to
ADDED | Business and data analyst module | SQL at depth (Wk2), analyst craft with business metrics, basket analysis, cohort and funnel, forecasting (Wk4), and Build 1 as an analyst-style data-to-insight project | Proposed change 1: widespread role, pays well
ADDED | Forward Deployed Engineering block | Roughly 30 hours at Wk16 running into the capstone: problem framing, solution thinking, trade-offs, quantified options, POC pitch. FDE method also becomes the operating mode of every build week | Proposed change 2: decision already made
ADDED | AI-free proctored evaluation | Weekly coding test and on-the-spot business case studies run observed, with no assistant. Alternates with theory and hands-on activity | Proposed change 5; key issue 2 and 3
ADDED | Live demo and defence, graded | Every build week ends in a live demo where the student codes or presents on the spot and defends the work | Rejection reason: failed the live demo
ADDED | Cross-domain transfer drill | The same technique applied across healthcare, retail, hyperlocal delivery and fintech, changing the metric, the constraint and the cost of an error | Foxo, Amnex and Landmark all probed domain application
ADDED | Challenges log on every project | Students record what broke, what they tried and what changed, as they go. This becomes the answer to how you handled and rectified issues | Other issue 1: practitioner questioning
ADDED | HR, behavioural and articulation coaching | Talking about yourself accurately; project narrative selection; what not to oversell; coached through weeks 19 and 20 and rehearsed in every mock | Other issue 3; mocks never crossed 50 percent
ADDED | Interview mindset and funnel briefing | How the funnel actually works, expected conversion, early interviews as calibration, and honest self-positioning | Overselling caused avoidable rejections
ADDED | Excel for analysts, one day | Pivots, lookups and presenting a number, used as a demonstration medium rather than a course | Landmark tested Excel; cohort 1 never covered it properly
ADDED | Monthly guesstimate or short interview | Low frequency, for structured thinking under pressure | Agreed in review at low frequency
ADDED | JD-driven domain prep loop | Job descriptions received in advance drive a preparation slot before each interview | Other issue 2
CUT | Computer Vision | Excluded entirely. Not taught, not claimed, not positioned for | Proposed change 3: different approach and skill set
CUT | Platform-level agentic orchestration | Multi-agent infrastructure and platform build-out removed. Agent development and productionalising agents are kept and deepened | Above the 0 to 3 year hiring band
CUT | Heavy standalone MLOps | Reduced to production essentials inside the agents-in-production week | Proposed change 4: time-consuming, low placement return
CUT | Classical NLP as a standalone block | Becomes a pre-read plus one focused day inside the transformers week | Proposed change 4
CUT | Standalone cloud and infrastructure block | Folded into deployment and monitoring where it is actually used | Proposed change 4
CUT | Evaluation count | Assessment types changed rather than added. Net number of graded events per week is unchanged | Key issue 4: too many evaluations that do not align
DEEPENED | SQL and data manipulation | Taught to the standard an experienced interviewer probes: join semantics, window functions, validation, on-the-spot querying | Landmark-style questioning
DEEPENED | Agent development and productionalising | Two full weeks: building agents, then trajectory evaluation, guardrails, recovery, deployment | These are the actual engineering roles being hired
DEEPENED | RAG with evaluation | Two weeks including a measured evaluation harness and mandatory citations | The baseline skill in current interviews
DEEPENED | Coding under pressure | Weekly, observed, assistant-free, short format | Key issue 3
REFRAMED | Foundations presented as data-analysis-led | Statistics, mathematics and machine learning delivered through data analysis, with Python and SQL inside it and case studies throughout | Agreed framing for leadership review
REFRAMED | Candidate positioning | Presented as strong entry-level with applied project depth, up to six to eight months equivalent, and never as experienced | Other issue 1
REFRAMED | Programme name | Curated for Forward Deployed AI Engineer Roles added to the programme name | Confirmed by programme head
Hours and credits are unchanged at 510 hours and 33 credits, so the Senate proposal does not need re-reconciling for this revision.

## Role Tracks
Cohort 2 ¦ Role tracks the programme actually serves
Honest coverage. Two primary tracks, two supported, one fitment layer, one deliberate exclusion.
Role track | Priority | What the role asks for | Where it is covered
GenAI / AI Engineer | Primary | LLM internals, prompting, RAG design and evaluation, cost and latency judgment, production reliability | Wk 7-12, 14
Agentic AI Engineer | Primary | Agent development, tool design, trajectory evaluation, guardrails, deployment | Wk 13-15
Data Analyst / Business Analyst | Supported | SQL at depth, business metric design, basket and cohort analysis, Excel fluency, stakeholder communication | Wk 1-4, Build 1
Data Scientist (entry) | Supported | ML core, honest evaluation, feature work, experiment design | Wk 4-6
Forward Deployed Engineer | Fitment layer | Problem framing, solution options with trade-offs, quantified recommendation, client-facing communication | Wk 16, and every build week
Computer Vision | Excluded | A different teaching approach and skill set. Cannot be added inside five months alongside the tracks above | Not covered, not claimed
HOW TO READ THIS
Primary | The programme is designed for these. Every student should be interview-ready here.
Supported | Genuinely covered and interviewable, sharing the same data and ML spine rather than running as a separate track.
Fitment layer | A way of working layered on top of the technical content. It improves performance in AI engineer, analyst and consulting-flavoured interviews, and opens forward deployed roles where companies hire at entry level. Most forward deployed openings still ask for client-facing experience, so it is positioned as fitment and not as a guarantee.
Excluded | Deliberately out of scope, recorded so nobody positions candidates into it.

## Assessment Model
Cohort 2 ¦ Assessment Model (revised)
Same five components and the same number of graded events per week. What changed is what happens inside them.
Component | Weight | How it works now
Mock interviews (5) | 30% | One per build week. Half technical, half a viva on that week's project, and each now closes with a live demo where the student presents and defends on the spot. Behavioural and HR questioning included from Mock R3. Fixed rubric, industry assessor, grades close the same week.
Major exams (3) | 25% | Theme-based: statistics, data, analyst techniques and ML (Wk5); deep learning through generative AI (Wk10); RAG, agents and production (Wk15). All conclude by Week 15.
Applied assessments | 25% | Weekly proctored coding with no assistant, alternating with an on-the-spot business case study. Automated grading where possible, best-of-N counts. This replaces the old weekly test and coding slot rather than adding to it.
Mini-projects + capstone | 15% | Five build-week mini-projects plus the capstone. Each now requires a challenges log and a live demo, so the work can survive practitioner questioning.
Participation | 5% | Daily Kahoot, group discussions, and a monthly guesstimate or short interview for structured thinking.
TOTAL | 100% | Weights remain a proposal awaiting sign-off.
AI-USE POLICY, STAGED
Weeks 1-6 | Core exercises and all assessments are assistant-free. The habit of thinking first is built before any tool is allowed.
Weeks 7-15 | Assistants permitted on build work, and every line must be defended in the viva. All graded coding and case studies stay assistant-free and observed.
Weeks 16-20 | Assistants used as accelerators with disclosure. The capstone defence assumes the student can justify every decision without help.
WHAT THE PLACEMENT REVIEW CHANGED
Interview finding |  | Assessment response
Failed the live demo, could not present on the go |  | Live demo and defence added to every build week and graded
Could not apply knowledge in the interviewer's domain |  | Cross-domain transfer drill and on-the-spot business case studies
Projects and presentations leaned on assistants |  | Staged AI-use policy; assistant-free proctored coding weekly
Could not describe how they handled real issues |  | Challenges log required on every project and used as interview material
Articulation weak; mocks never crossed 50 percent |  | Behavioural and HR questioning inside mocks from R3; coaching in weeks 19 and 20
Too many evaluations that did not match placement |  | Assessment types replaced, not added. Weekly graded-event count unchanged

## Build Week Ops
Cohort 2 ¦ Build Week Anatomy
One powerful week every three weeks. No new content. Build, speak, think, and defend. Everything closes in-week.
Days 1-3 | Mini-project on a prescribed, named-customer brief with a constraint built in. Challenges log kept live through the build.
Days 4-5 | Mock interview, half technical and half a viva on the project. Offline presentation. Impromptu group discussion. Live demo where the student codes or presents on the spot.
FDE mode | Every brief is run the way a forward deployed engineer would run it: frame the problem, shortlist options, state the trade-off, recommend with numbers.
Also serves as | The breather, recap and portfolio week, which is what students asked for in cohort 1.
Grade closure | Mock, project, presentation and demo grades all close within the week on a fixed rubric. Non-negotiable for assessors.
Bias control | Fixed rubric removes interviewer bias. Assessors commit to in-week closure or are not engaged.
Mode | Online and offline mix. Mocks can run online, presentations are offline, offline visits capped at one to two days per assessor.
BUILD WEEKS AND ASSESSORS (internal planning)
Build week | Assessor
Build 1 (Wk3) - Data-to-Insight | Ishu
Build 2 (Wk6) - ML mini | Anupam
Build 3 (Wk9) - DL / LLM mini | Sumit Shukla
Build 4 (Wk12) - RAG mini | Anish
Build 5 (Wk15) - Agentic mini | Sameer
Assessor names are for internal planning and are removed before any institution-facing version.

## Hours
Cohort 2 ¦ Hours (unchanged)
10 theory hours = 1 credit; 20 practical hours = 1 credit. Matches the Senate proposal exactly.
Component | Hours | Credits | Note
Concept building (theory) | 150 | 15 | Includes institution faculty sessions
Practical / hands-on | 300 | 15 | Labs, build weeks, drills, case studies, mocks
Capstone project | 60 | 3 | Weeks 16-18, scoped in FDE mode
TOTAL | 510 | 33
The revision reallocates content inside the same 20 weeks. No change to hours or credits, so the Senate submission is unaffected by this curriculum revision.